## Slide 1: Assistive Technology presentation to Co-production Network

## Slide 2: Co-production Network – Assistive Technology Project Agenda
Our journey so far
Vision and Design principles
List of projects and pilots
Milestones
Outcomes and benefits
Our ask of the CPN
Next steps

## Slide 3: Our journey so far
Diagnostic exercise completed. Key recommendations:
Design and embed a new service model
Develop a clear vision, strategy and business case
Design a new referral pathway
Establish clearly defined eligibility criteria
Define governance and decision making
Establish a strong collaborative partnership with suppliers
Create approach to measure financial and non-financial benefits
Deliver an ongoing programme of culture change and engagement
Progress made since the diagnostic:
    Project team assembled
    Vision and design workshops completed with key staff
    Communication and engagement plan created
    Logo and design work completed
    First staff newsletter issued

## Slide 4: Vision and Design principles

## Slide 5: Assistive Technology Project Structure
Key:
Primary project – designing the future model for all
Identified specific pilot groups to achieve short term savings
Assistive Technology Project Team
Learning Disability
Equipment Return
Hospital Discharge / reablement
Supported Living
Autism pilot
Care Home
Community
Locality
Digital alarm pilot
1-2-1 in residential care
Target Operating Model Design
Process design (inc resources & training)
Comms and engagement
Top client contacts

## Slide 6: Assistive Technology Project Structure – Main Project
Target Operating Model Design
Owner: Vicky & Ilona
Goal:
Create and embed new ways of working to maximise utilisation of assistive technology in Slough to achieve financial savings through reduction, avoidance or delay in requirement for services.
Key activity:
Review eligibility criteria
Review strategy document
Detailed process design
Develop staff training and learning offer
Develop financial tracking
Communication & Engagement
Owner: Vicky
Goal:
Effectively communicate changes to all stakeholders, generate buy-in and create momentum for project activity to embed new ways of working for all.
Key activity:
Invite co-production network
Work with comms to create design and branding
Create monthly newsletter
Tailor comms to each mapped stakeholder group throughout

## Slide 7: Assistive Technology Project Structure – Pilot Schemes (1)
Learning Disability
Supported Living
Goal: Identify providers and explore how technology can reduce placement costs for clients placed in those settings
Autism Support
Goal: Identify innovative technology solutions to provide structure and support without the need for formal care arrangements
Equipment return
Care Home
Goal: Work with NRS to facilitate return of equipment in care homes no longer in use to obtain recycling credits
Community
Goal: Understand use of equipment in the community and facilitate return of items no longer used or needed

## Slide 8: Assistive Technology Project Structure - Pilot Schemes (2)
Locality
Digital alarm pilot
Goal: Review clients currently with a pendant alarm to identify opportunities to use technology to reduce care packages
1-2-1 in Residential
Goal: Review clients in residential settings that are als0 receiving 1-2-1 support and identify opportunities for saving
Top client contacts
Goal: Understanding the people that make frequent contact, review and consider technology that can support and reduce formal care where possible
Hospital
Hospital discharge
Goal: Design improved pathways to utilise technology to reduce placements, using pilot group to demonstrate the impact

## Slide 9: Milestones 2023/24
January | February | March
Revise eligibility criteria High level process design Develop financial tracking NRS training session Begin reviews for pilot client groups Engagement with Berks LA’s | Detailed process design Detailed data review Roll out of training Continue to review and identify savings for pilot groups Create case studies and library of evidence Finalise training materials using personas | Training and embedding Complete work on pilot groups Initial case audits to check tracking and impact

## Slide 10: Outcomes and benefits expected
      Increasing independence and choice for residents
      Increase in service users returning home after hospital stays
      Improvement in the customer experience
      Improved process for staff
      Support for carers
      Avoidance of low-cost care packages such as medication and prompting
      Lower volume and cost of care packages
      Delaying the need for interim and permanent residential placements
      Reduction in 1-2-1 support hours – less intrusive support where appropriate and enabling people to meet their outcomes.

## Slide 11: Our ask of the Co-production Network
A clear objective of SBC is to regularly and effectively engage with our community to make sure that our services are fit for purpose and align with our aspirations to increase independence and choice.
We would like the co-production network to be actively involved the design and communication of our new assistive technology Target Operating Model to play a critical friend role and ensure that our new ways of working is accessible and easy to use for residents, and to make sure that we are communicating changes as widely and effectively as possible.
This will involve:
Attending the project team meeting each fortnight
Reviewing processes from the residents’ perspective
Contributing to the communication strategy and content of external communications

## Slide 12: Next steps
We will be back to provide a detailed progress update at the next meeting before our external communication begins in April.