## Instructions
Guidance on completing the 2025/26 Delivery Plan template
Header: The name of the LTA (or LTAs) should be added so that the header reads "ANYTOWN COUNCIL BUS SERVICE IMPROVEMENT DELIVERY PLAN 2025/26"
Category of scheme/measure: should be chosen from the drop-down list in the spreadsheet cell. If a scheme falls into more than one category then category under which the majority of benefits arise should be selected. If that is not possible, classify the scheme as 'Other' and then provide an explanation in the 'Additional Description' field. Alternatively, consider whether the scheme is a single scheme.
Name of scheme/measure: must capture the essentials of what it is and where it is (where appropriate) without being too long or too short, for example 'High St Anytown bus lane', 'Anytown area all-operator weekly ticket'. Scheme names used should be identifiable against the names used in the 2024 BSIP document and (where appropriate) the EP Scheme and, for schemes using previous years' BSIP funding, the scheme names that have been used throughout programme delivery reporting to date. Having said this, the opportunity can be taken to refine/improve names to add useful detail on what and where the scheme or measure is. All bus service improvement schemes and measures which will be delivered in 2025/26 or 2026/27 should be listed, including schemes which are being funded from previous years' DfT BSIP funding or any other funding source - the scheme funding mix should be clarified in the appropriate columns. For capital schemes, all schemes that will be started or completed and opened in 2025/26 should be listed. Schemes in the 2024/25 programme which have been completed and opened, and on which there will be no further spending in 2025/26 should not be listed. For revenue schemes, all schemes that will be or are planned to be running in 2025/26 or 2026/27 should be listed. This should include bus service support schemes that will be spending previous years' DfT BSIP funding.
Additional description of scheme/measure (including intended beneficial outcomes): this field is for useful additional description of the scheme/measure that is not captured in the scheme name. This description is an opportunity to describe the scheme outputs (for example, "200m bus lane on High St Anytown plus traffic signals bus detection and priority at High St/Market St saving on average 20 seconds per bus and up to 5 mins per bus at time of peak traffic congestion on corridor carrying 8 buses/hour"; "£5 discount on £17 commercial fare for all-operator weekly ticket covering all services in the Anytown area bus network"). It should also contain an initial assessment of the intended beneficial outcomes from the scheme or measure. To the maximum extent possible, these should be quantified. For example, "The High St Anytown bus lane aims to save 200 minutes of bus delay time per week, and improve punctuality on routes 2, 7 and 87A by 5 percentage points." Or, "Target is sales of 10,000 Anytown all-operator weekly tickets per 4 week period, saving passengers £650k per year". The description of the intended beneficial outcomes should describe how the scheme/measure contributes towards delivery of the objectives of the 2024 BSIP.
Target delivery date: For capital schemes, this should be the date the scheme (infrastructure or equipment) is commissioned and opens for use by the public. For revenue schemes: This should be the date the scheme commences e.g. the date a fares scheme or bus service contract is live and in use by passengers. This target date will be the baseline for subsequent quarterly monitoring and reporting. For funding allocated in 2022-23, 2023-24 and 2024-25, through Phases 1, 2 and 3 of the BSIP Programme, the specified period is March 2025 for fares schemes; and March 2026 for all other revenue schemes (e.g. service support) and all capital schemes. For Bus Grant funding allocated in this letter, the specified period means March 2027 for all schemes, both revenue and capital. We strongly encourage you to use the Bus Grant funding by March 2026 in order to deliver benefits to passengers and communities as quickly as possible. We recognise, however, that it will not always be fully possible to do so, or to do so in a value for money manner, given the lead times on capital projects and usual lengths of tendered bus service contracts. Where absolutely necessary funding can therefore be carried forward into 2026/27. As the Department cannot provide funding in advance of need this is only appropriate where you are satisfied that without having received the payment in 2025/26 your Authority would not have been able to progress Delivery Plans or enter into contracts (either in absolute terms or at an appropriate cost and value for money). In all cases we would expect a contractual or other significant commitment to have been entered into for the full use of the funding by March 2026. You should maintain a clear record of the rationale, and where relevant VfM or cost benefits achieved, and decisions to use this funding beyond 2025/26 – which should be signed off by your Chief Finance Officer (or equivalent). A copy of any such record should be submitted with your next quarterly return when it is created or amended.
Budget/estimated cost columns: These columns should be £k numbers, separating out capital and revenue funding. (In the majority of cases it is expected that the scheme funding will either be all capital or all revenue funding.) The funding of the total scheme cost should be broken down into that finded by 2025/26 DfT Bus Grant for Local Authorities, previous years' DfT BSIP funding, and all other funding sources. The final column should be used to identify the other funding sources (DfT or other).

## Delivery Plan
SLOUGH BOROUGH COUNCIL Bus Service Improvement Delivery Plan 2025-26
Category of scheme/measure [select from drop down list] | Name of scheme/measure | Additional description of scheme/measure (including intended beneficial outcomes) | Target delivery date | Budget/estimated cost (£k) |  |  | (of which) 2025-26 Bus Grant (£k) |  |  | (of which) previous years' DfT BSIP funding (£k) |  |  | (of which) Other funding (£k) |  |  | Notes on other funding sources (identifying non-BSIP funding)
|  |  |  | Capital | Revenue | Total | Capital | Revenue | Total | Capital | Revenue | Total | Capital | Revenue | Total |  | check | check
Bus service support/network development | Additional evening and Sunday services | Additional and continued grant funding of services from a number of areas in Slough; joint with Buckinghamshire Council, Heathrow Airport Ltd and Royal Borough of Windsor & Maidenhead. Customer satisfaction and patronage | Apr 25 - Sep 25 |  | 333449 | 333449 |  | 147278 | 147278 |  | 148159 | 148159 |  | 38012 | 38012 | Contribution by Heathrow Airport Ltd; other LTA funding also expected to be drawn from BSIP allocations | 333449 | 0
Bus service support/network development | Access to Wexham Park Hospital | Additional evening and Sunday services; new route expanding direct bus access to the hospital; joint with Buckinghamshire Council and Royal Borough of Windsor & Maidenhead. Customer satisfaction and patronage | Apr 25 - Jan 26 |  | 281174.5 | 281174.5 |  | 130299.5 | 130299.5 |  | 150875 | 150875 |  |  | 0 |  | 281174.5 | 0
Bus service support/network development | Capacity enhancements | Address reported issues of overcrowding on one service; joint with Buckinghamshire Council. Customer satisfaction and patronage | 2025-09-01 |  | 120360.25 | 120360.25 |  | 67860.25 | 67860.25 |  | 52500 | 52500 |  |  | 0 |  | 120360.25 | 0
Simpler/more affordable fares | Multi-operator ticketing scheme | A multi-operator scheme providing for cross-acceptance of tickets and interchange journeys. Particular benefit to access to Wexham Park Hospital. An allowance is made in the costing for subsidy to reduce fares. Customer satisfaction and patronage | 2026-01-01 |  | 160000 | 160000 |  | 160000 | 160000 |  | 0 | 0 |  |  | 0 |  | 160000 | 0
| Christmas fares promotion | Free travel 4 Saturdays before Christmas (joint with RBWM) | 2025-12-01 |  | 50000 | 50000 |  | 50000 | 50000
Bus stops/stations/interchanges | Town centre bus interchange wayfinding | Develop a wayfinding scheme between Slough rail station and Slough town centre interchange bus stops. Customer satisfaction and patronage | 2026-01-01 | 125000 | 25000 | 150000 | 100000 |  | 100000 |  | 25000 | 25000 | 25000 |  | 25000 | Contribution by GWR under the Stations Fund (subject to confirmation) | 25000 | 0
Bus stops/stations/interchanges | Bus stop development | Accessibility upgrades to 4 identified bus stops where current provision is poor, with further stops to be identified. Customer satisfaction and patronage | 2026-01-01 | 75000 | 10000 | 85000 | 75000 |  | 75000 |  | 10000 | 10000 |  |  | 0 |  | 10000 | 0
Bus priority infrastructure | Marginal gains | Identify and deliver small-scale highway schemes to improve bus journey times and punctuality with a focus on cross-town service 7 (Heathrow Airport - Britwell). Potential improvements to highway scheme management. Journey time, punctuality, patronage, customer satisfaction | 2026-01-01 | 225000 | 90000 | 315000 | 225000 |  | 225000 |  | 90000 | 90000 |  |  | 0 |  | 90000 | 0
Bus stops/stations/interchanges | Slough town centre bus interchange bus stops | Improvements to pedestrian access to bus stops; increase in bus stop and stand capacity; Real Time Passenger Information. Punctuality, patronage, customer satisfaction | 2026-01-01 | 250000 | 100000 | 350000 | 225000 |  | 225000 |  | 100000 | 100000 | 25000 |  | 25000 | Contribution by GWR under the Stations Fund (subject to confirmation) | 100000 | 0
Bus stops/stations/interchanges | Slough town centre bus interchange medium-term strategy | Develop medium to long-term strategy for bus and multi-modal interchange in Slough town centre. Journey time, punctuality, patronage, customer satisfaction. | 2026-01-01 |  | 50000 | 50000 |  |  |  |  | 50000 | 50000 |  |  |  |  | 50000 | 0
Vehicles | Zero-emission bus and depot strategy | Develop feasibility study for bus and depot electrification. Patronage, customer satisfaction. | 2026-01-01 |  | 50000 | 50000 |  |  |  |  | 50000 | 50000 |  |  |  |  | 50000 | 0
Bus priority infrastructure | Traffic signal priority | Repair existing detection systems at selected junctions heavily used by buses; develop system for providing signal priority at selected junctions. Journey time, punctuality, patronage, customer satisfaction. | 2026-01-01 | 292715 | 10000 | 302715 | 292715 |  | 292715 |  | 10000 | 10000 |  |  |  |  | 10000 | 0
LTA delivery/admin costs | Officer and consultancy delivery support | Officer and consultancy delivery support | 2026-03-01 |  | 63000 |  |  | 63000
|  |  |  | 967715 | 1342983.75 | 2247698.75 | 917715 | 618437.75 | 1473152.75 | 0 | 686534 | 686534 | 50000 | 38012 | 88012 | 0 | 0

## Scheme categories list
Category of scheme/measure
Bus priority infrastructure
Bus stops/stations/interchanges
Other infrastructure
Vehicles
Ticketing equipment/systems
Bus service support/network development
Simpler/more affordable fares
Safety and security
Improved information, marketing
Development of future proposals
LTA delivery/admin costs
Other